Date: 15 February 2025
Team ID: SWTID-2026-2896
Project Name: Script-Controlled ACL – Restrict Record Access Based on Field Value

1.Product Backlog, Sprint Planning and Estimation

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Table Setup | USN-1 | As an administrator, I want to create the Institution Details table to store student and faculty information. | 3 | High | Project Team |
| Sprint 1 | Role Management | USN-2 | As an administrator, I want to create roles bb1, bb2, bb3, and bb4 and assign them to users. | 3 | High | Project Team |
| Sprint 1 | Read Access Control | USN-3 | As an authorized user, I want to view permitted institution records based on my role and branch. | 3 | High | Project Team |
| Sprint 2 | Create Access Control | USN-4 | As a user with role bb2, I want to create institution records. | 2 | High | Project Team |
| Sprint 2 | Write Access Control | USN-5 | As a user with role bb3, I want to update permitted institution records. | 2 | High | Project Team |
| Sprint 2 | Delete Access Control | USN-6 | As a user with role bb4, I want to delete records when authorized. | 2 | High | Project Team |
| Sprint 3 | Administrator Access | USN-7 | As an administrator, I want full access to institution records. | 2 | High | Project Team |
| Sprint 3 | Security Testing | USN-8 | As a tester, I want to verify that authorized and unauthorized users receive the correct access permissions. | 3 | High | Project Team |
| Total |  |  |  | 20 |  |  |

Sprint Schedule

| Sprint | Main Tasks | Duration | Planned Story Points |
| --- | --- | --- | --- |
| Sprint 1 | Create table, fields, roles, and Read ACL | 6 days | 9 |
| Sprint 2 | Configure Create, Write, and Delete ACLs | 6 days | 6 |
| Sprint 3 | Configure admin access and complete security testing | 6 days | 5 |
| Total | Implementation and testing | 18 days | 20 |

2. Project Tracker

| Sprint | Total Story Points | Duration | Planned Start | Planned End | Completed Points (Target) | Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | 9 | 6 days | Day 1 | Day 6 | 9 | Day 6 |
| Sprint 2 | 6 | 6 days | Day 7 | Day 12 | 6 | Day 12 |
| Sprint 3 | 5 | 6 days | Day 13 | Day 18 | 5 | Day 18 |
| Total | 20 | 18 days |  |  | 20 |  |

Note: These are planned targets. Enter actual dates and completed points after the project work.

3. Team Velocity

Velocity is the number of story points completed during a sprint.

Formula:

Average velocity per day = Total story points ÷ Total sprint days

= 20 ÷ 18

= 1.11 story points per day (approximately).

If using the template's example of a 10-day sprint with 20 story points, the velocity is 2 story points per day.

4. Burndown Chart

The burndown chart shows the remaining work during project development.

| Project Day | Planned Work Remaining (Story Points) |
| --- | --- |
| Day 1 | 20 |
| Day 3 | 17 |
| Day 6 | 11 |
| Day 9 | 8 |
| Day 12 | 5 |
| Day 15 | 3 |
| Day 18 | 0 |

The target is to reduce the remaining work to zero story points by Day 18.

5. Sprint Burndown Diagram